## Tasks
# | Work Item | Component | Description | Status/ETA | Repo State | Actual Work Required
1 | MigTD changes to support GHCI_20260114 | MigTD | (Old) Rebind flows, servtd_ext along with InitMigTD data | Done | Present — rebinding.rs, servtd_ext.rs, InitData struct, RATLS cert extensions, SPDM VDM elements all implemented | None — fully implemented
2 | VMM changes to support Servicing MigTD | VMM | Add support to bring up new service MigTD | Done | N/A — VMM component, not in this repo | None — outside this repo
3 | VMM changes to support rebind flows | VMM | Add in-place memory packet exchange flows in VMM | Done | N/A — VMM component, not in this repo | None — outside this repo
4 | Integration/Debug of MigTD flows with VMM support on Rebind | VMM+MigTD | Verify end-to-end rebind flow with MigTD and VMM support | Done | N/A — integration testing, not tracked in repo | None — outside this repo
5 | Verify TDX module with Rebind Support | TDX Module | Running into module hang during TDH.SERVTD.REBIND due to xcr0 restore. Received fix for EMR, working on SPR verification. | WIP/few days | N/A — TDX Module component, not in this repo | None — outside this repo
6 | Verify Migration with Rebind done TD | VMM | Ensure migration is successful with new MigTD after rebinding | Not Started/few days | N/A — VMM component, not in this repo | None — outside this repo
7 | MigTD changes to support GHCI_20260213 | MigTD | 1. Clean up prepare/finalize phase 2. Support updated rebind flows 3. Cleanup and update MigTD with new MIGTD_DATA_ENTRY_STRUCT 4. Update MigTD flows w.r.t policy verifications and SERVTD_EXT verifications | Not Started/~2 weeks | Not done — prepare/finalize phases still active (MIGTD_REBIND_OP_PREPARE/FINALIZE in rebinding.rs). MigtdDataEntry & policy/SERVTD_EXT verification exist but need updating per new spec | Remove PREPARE/FINALIZE phase split in rebinding.rs; update MigtdDataEntry fields and parsing to match GHCI_20260213 spec; update policy verification and SERVTD_EXT validation logic per new spec; update RATLS cert extensions and SPDM VDM message elements accordingly
8 | VMM clean up on old Rebind flows, support new flows | VMM | Remove prepare/finalize phases and support new MigTD flows | Not Started/~1 week | N/A — VMM component, not in this repo | None — outside this repo
9 | Integration/Debug of MigTD flows with VMM support on updated Rebind | VMM+MigTD | Verify end-to-end rebind flow with MigTD and VMM support | Not Started/~1 week | N/A — integration testing, not tracked in repo | None — outside this repo
10 | Miscellaneous: Provisional log support | MigTD | Ensure logs prior to EnableLogArea are saved and provided in shared memory during EnableLogArea. Completed feature and working on unit test case fix. | WIP/few days | Present — dual-buffer system in logging.rs (PROVISIONAL_LOGAREAPTR + LOGAREAPTR), enable_logarea() copies provisional→shared, unit tests exist | Fix failing unit tests for provisional logging
11 | Miscellaneous: DCAP library logs | MigTD | Provide log support for DCAP library as per MSFT request. Not heard back from MSFT on priority or Quoting Enclave steps. | Deferred | Not present — only wrapper-level logging around DCAP calls, no hooks into the DCAP library itself | Deferred — awaiting MSFT priority; would require adding logging hooks/callbacks into DCAP library integration layer
12 | Miscellaneous: CoRIM/TOML format support | MigTD | MSFT updated this is not required | Deferred | Not present — zero CoRIM/TOML references; only JSON format supported for policies and collaterals | None — not required per MSFT